## Sheet1
Week | Task | Difficulty
2023-11-01 | Create spreadsheet of project plan | Easy
2023-11-03 | Create trello board | Easy
2023-11-05 | Create Git repo | Easy
2023-11-07 | Replace the scaffolding code with the flask code | Medium
2023-11-09 | Ensure the app runs locally without errors | Medium
2023-11-11 | Ensure the app runs in Cloud Shell without errors | Medium
2023-11-13 | Set up GitHub Actions | Hard
2023-11-15 | Add the GitHub Actions badge to the README | Medium
2023-11-17 | Create the App Service in Azure | Medium
2023-11-19 | Test the app running in Azure App Service | Medium
2023-11-21 | Set up the Azure DevOps pipeline | Hard
2023-11-23 | Create architectural diagram | Medium
2023-11-25 | Take screenshots demonstrating key steps | Easy
2023-11-27 | Create README file with full instructions of how to run the code | Medium
2023-11-29 | Create demo video and post to YouTube | Medium
Goals
2023-12-31 | Submit project
* here the tasks are planned on daily basis, however in real project due to complexity of tasks and planning a quarterl and yearly plan has to be done, --> For each week deliverables have to be defined,